## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1783778 |  |  | Week starting: | 10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-17 | 19:00 | 23:00 | 4 | Compare the search results from Microsoft Teams Shifts and course planner. | To get the difference between information from Microsoft Teams Shifts and course planner. | Outcome: Get the error information from Microsoft Teams Shifts and highlight these information. Next action: Keep working on the search function.
Tuesday | 2021-05-18 | 19:00 | 22:30 | 3.5 | Keep working on the search function. | Search function can help user get what they want quickly. | Outcome: If cannot find a corresponding course information in Microsoft Teams Shifts, add missing status to the course from course planner. Next action: Testing plan.
Wednesday | 2021-05-19 | 13:00 | 15:00 | 2 | Testing plan. | Testing plan can help us improve our system and find out bugs. | Outcome: A number of test cases were written for the corresponding functions. Next action: Add more filters to our search function.
Thursday | 2021-05-20 | 14:30 | 17:30 | 3 | Weekly meeting and fix bugs in search function. | Show our system to our client and get some feedback. | Outcome: Bugs fixed. Next action: Improve our test plan.
Friday | 2021-05-21 | 13:00 | 15:00 | 2 | Improve our test plan. | Testing plan can help us improve our system and find out bugs. | Outcome: Done. Next action: Improve our system according to our client's feedback.
Saturday | 2021-05-22 | 13:00 | 18:00 | 5 | Improve our system according to our client's feedback. | We need to add username for the corresponding course in Microsoft Teams Shifts. | Outcome: Improved our user interface to be more user friendly. Next action: Test our system.
|  |  | Total | 19.5