## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1783778 |  |  | Week starting: | 11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-24 | 18:00 | 22:00 | 4 | Review course materia. | Help me understand next step of our project clearly. | Outcome: Done Next action: Test our system and fix bugs.
Tuesday | 2021-05-25 | 18:00 | 22:30 | 4.5 | Test our system and fix bugs. | Testing can help us improve our system. | Outcome: Change the date comparsion function to make our system run faster. Next action: Keeping testing our system.
Wednesday | 2021-05-26 | 13:00 | 17:00 | 4 | Keeping testing our system. | Testing can help us improve our system. | Outcome: Some changes has been added to the get shift function and compared results have been stored in cache so I should improve the search function. Next action: Improve the search function and attend weekly meeting.
Thursday | 2021-05-27 | 13:30 | 17:30 | 4 | Improve the search function. | Show our system to our client and get some feedback. | Outcome: Delete the comparsion function in search function and get compared results from cached information. Next action: Improve the layout of our system.
Friday | 2021-05-28 | 13:00 | 14:00 | 3 | Improve the layout of our system. | To make our system more user-friendly. | Outcome: Done. Next action: Prepare for the poster of our system.
Saturday | 2021-05-29 | 13:00 | 18:00 | 5 | Prepare for the poster of our system. | Poster can help our clients get familiar with our system. | Outcome: We will work together next Monday to draw the poster. Next action: Draw the poster.
|  |  | Total | 24.5