## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1783778 |  |  | Week starting: | 12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-31 | 12:00 | 18:00 | 6 | Working on the final poster. | Poster can help us introduce our system to our client clearly. | Outcome: Finishing the introduction, tools, and system overview part of the poster. Next action: Test our system and fix bugs.
Tuesday | 2021-06-01 | 18:00 | 22:30 | 4.5 | Test our system and fix bugs. | Testing can help us improve our system. | Outcome: New developer account of Microsoft cannot log in to our system successfully. Next action: To find a method to run our system by one line commond.
Wednesday | 2021-06-02 | 13:00 | 16:00 | 3 | To find a method to run our system by one line commond. | To implement this function, it will be easy to run our system. | Outcome: We decided to deploy our system on a cloud server. Next action: Attend weekly meeting.
Thursday | 2021-06-03 | 14:30 | 17:30 | 3 | Attend weekly meeting. | Show our system to our client and get some feedback. | Outcome: We needed to find another way to run our system because our client doesn't want us to deploy our system on cloud server. Next action: Find another way to run our system.
Friday | 2021-06-04 | 13:00 | 15:00 | 2 | Find another way to run our system. | To implement this function, it will be easy to run our system. | Outcome: We are going to add all packages needed to the manage.py fileso that all packages will be installed automatically when we run this file. Next action: Record the poster presetation video and prepare for the final report.
Saturday | 2021-06-05 | 13:00 | 20:00 | 7 | Record the poster presetation video and prepare for the final report. | Poster can help our clients get familiar with our system. | Outcome: Wait for my teammates' presentation videos and combine these videos together. Next action: Work on the final report.
|  |  | Total | 25.5