## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1783778 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 18:00 | 22:00 | 4 | Review week 1 lecture, and make clear what we should do this semester | I can have a better understanding about this course | Understand the abstract about this project
Tuesday | 2021-03-09 | 15:30 | 21:30 | 6 | Do research about Microsoft Team Shift. | We are asked to use this technology to finish this project. | Microsoft Team Shift provides third_party API
Wednesday | 2021-03-10 | 16:00 | 22:00 | 6 | Review the framework React | React is an excellent framework to develop a website | join the weekly meeting
Thursday | 2021-03-11 | 14:00 | 15:00 | 1 | Weekly meeting | Get more information about this project from the client | We need to discuss with team 8 and divide this project into two parts.
Friday | 2021-03-12 | 15:00 | 21:00 | 6 | Do research about this project(Microsoft Team Shift and how to get information from course planner website) | To find out which part do I want to do | On my opinion, I prefer the API part of this project
Saturday | 2021-03-13 | 15:00 | 17:00 | 2 | Split the task with team 8 | We can work out which part of this project are we supposed to do | We are going to do the first part(The API part)
|  |  | Total | 25