## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1783778 |  |  | Week starting: | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 |  |  |  | public holiday
Tuesday | 2021-04-06 | 18:00 | 22:30 | 4.5 | Learn how to use python to draw a dashboard | Our system will use a dashboard to show data | Found a tool called GUI
Wednesday | 2021-04-07 | 14:00 | 18:00 | 4 | Login in to Microsoft Team APP and Learn how it works | Our system is aimed to get data from Microsoft Team | Maybe we can build our system as a plugin of Microsoft Team
Thursday | 2021-04-08 | 14:30 | 3:30 | 1 | Weekly meeting | Keep track of the project | reported our process to the client and decided the chair person of next meeting
Friday | 2021-04-09 | 13:30 | 16:30 | 3 | Reviw pitch presentation videos of group B | Watch other groups' presetation can help us improve ourself | Completed
Saturday | 2021-04-10 | 13:00 | 17:00 | 4 | Try to get data from Mcirosoft Team shift through API | Our system is aimed to get data from Microsoft Team | still trying
|  |  | Total | 16.5