## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1783778 |  |  | Week starting: | 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Tuesday | 2021-04-11 | 17:00 | 23:00 | 6 | Figure out why I cannot login to our system using my Microsoft developer account. | We can gain access to Microsoft API using developer account. | Outcome: There are some problems with my account so that I will keep using my teammate's account. Next action: Add search function to our system.
Wednesday | 2021-05-12 | 18:00 | 22:30 | 4.5 | Build user interface for search function. | Search function can help user get what they want quickly. | Outcome: UI is completed. Next action: Search information from course planner.
Thursday | 2021-05-13 | 11:00 | 16:00 | 5 | Search information from course planner. | Search function can help user get what they want quickly. | Outcome: Gain more information from our client. Next action: Add more filters to our search function.
Friday | 2021-05-14 | 19:00 | 22:00 | 3 | Add more filters to our search function. | Search function can help user get what they want quickly. | Outcome: Add semester and session filter to the search function. Next action: Search information from course planner.
Saturday | 2021-05-15 | 13:00 | 16:00 | 3 | Search information from course planner. | Search function can help user get what they want quickly. | Outcome: Successfully get information from course planner. Next action: Search information from Microsoft Teams shifts.
Sunday | 2021-05-16 | 13:00 | 16:00 | 3 | Search information from Microsoft Teams shifts. | Search function can help user get what they want quickly. | Outcome: Successfully get information from Microsoft Teams shifts. Next action: Compare the search results from both sides.
|  |  | Total | 24.5