## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-05-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-03 | 18:00 | 23:30 | 5.5 | Finish the testing plan. | It's part of the curriculum. | Finished the testing plan. Next, I will Modify the crawler
Tuesday | 2021-05-04 | 9:00 | 11:00 | 2 | Adjust the web-scraper | Our system needs to use the web scraper to get information on the course planner. Team 8 made some change to the web-scraper, and we have to integrate it into our system. | Intergrated the web-scraper into our system. Next, I will implement the function of comparing all shifts in Microsoft Teams.
Wednesday | 2021-05-05 | 12:30 | 18:30 | 6 | Adding the function of checking all shifts in user's Microsoft Teams. | The system is for user to check all his shifts in Microsoft Teams | When the user clicks on "shifts", our software will automatically check all the shifts in Microsoft Teams. Next, I will update the cache function in term of the course planner.
Thursday | 2021-05-06 | 12:00 | 17:00 | 5 | Implementing cache function of all courses data from the course planner. | Similarly to cache group name, caching course data from the course planner will significantly improve the performance since calling a web-scraper will cost lots of time. | Our system can cache all course data that have been searched. This greatly improved the performance(Search time reduced from 2 minutes to 10 seconds). Next, I will reorganize the code preparing for testing.
Friday | 2021-05-07 | 14:00 | 18:00 | 4 | Reorganized the code and weekly meeting | Readable and logical code can improve our testing efficiency and reduce the likelihood of errors | Improved code readability and extensibility, deleted unnecessary code and renamed lots of variables, added lots of comments.Next, I will implement the function of comparing session of classes.
Saturday | 2021-05-08 | 13:00 | 16:30 | 3.5 | Implementing comparing session type. | Our client requred this system to be able to check the session type of shifts | Implemented a function of checking the consistency for type of sessions. Next, I will start unit testing.
|  |  | Total | 26