## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-05-24
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 10:00 | 13:00 | 3 | unit testing | It is not possible to test a large piece of software at once, so we need to break the software into several units and test them separately | I tested get_token(), get_group_name(), get_user_name() and get_team() function. They work as precisely we expected. Next I will test other functions.
Tuesday | 2021-03-09 | 14:00 | 18:00 | 4 | unit testing | Some key functions like get_shift() should be tested more to make sure the core function would not crash the whole systems. | I tested delte_shift_byID(), search_courses() and get_shift() functions. I found some bugs in the test and I fixed them. Next I will do the system testing.
Wednesday | 2021-03-10 | 13:00 | 19:00 | 6 | system testing | While each functions works well when tested individually, we need to make sure that all the functions work together. | Tested the whole software with regular input and output starting from sign-in to delete all incorrect shifts. This includes getting shifts data, getting course data, check the data and delete wrong shifts. Next we will have a meeting with our client and I will improve the UI of our application.
Thursday | 2021-03-11 | 14:30 | 16:00 | 1.5 | Meeting with client. Discuss with our team members. | We need to report the progress to our client. | The client told us that this software is basically done, but we need to improve the UI and clean the code. These two things are what I will do next.
Friday | 2021-03-12 | 18:00 | 23:30 | 5.5 | Upgrade the UI and appearance of our application. | Our client required us to improve the UI and appearance. | Make use of Bootstrap to unify the software appearance model. I upgrade all the buttons, tables, input form of our web page. The information provided to a user is more straightforward. Next, I will add some useful links and guide information.
Saturday | 2021-03-13 | 12:30 | 19:00 | 6.5 | Improve the user interface and create a guide page. | It is essential to make our software easy to use for everyone; otherwise, it is meaningless to have our application functions. | Create a guide page to tell the user how to use our application. I also changed the logic of the user interface and added some useful links to the outside website like the course planner and Microsoft Teams. Next, I will clean our code.
|  |  | Total | 26.5