## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-05-31
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-03 | 12:00 | 19:00 | 7 | Packing the application and make a setup file. | Our client requires us to have the application packed and easy to boost. | I created a setup program that automatically installed the dependencies and packed this setup file into an executable file. Next, I will test this setup program.
Tuesday | 2021-05-04 | 18:00 | 23:00 | 5 | Testing the dependencies and getting all Python module used included. | We have to make sure that the setup program can automatically install all the Python environment that we need to run our program. | Use Pip to export all dependencies to a requirenment file. Then installed a Linux virtual machine and successfully install and run our program. Next, I will implement the function of deleting incorrect shifts.
Wednesday | 2021-05-05 | 13:00 | 17:00 | 4 | Writing the instruction file. | Our customers require us to provide a instruction file to tell the user how to install and use our application. | Write an instruction file that includes how to install and use our application. Next, I will deploy the updated application to the cloud server Heroku.
Thursday | 2021-05-06 | 9:00 | 15:00 | 6 | Deploying updated application and weekly meeting. | Now we have done the development and need to show a demo to our client. | An updated version of our web application has been deployed to Heroku.It includes improved appearance and a smarter matching algorithm. Next, I will update the poster and collect feedback from other team.
Friday | 2021-05-07 | 20:00 | 23:00 | 3 | Sending our application to other groups and test it. And update the software architecture part of the poster. | Testing on other team's computer can tell us whether our application can successfully install and run on other computers. | I updated some problems during testing on other teams' computers. Team 7 and other teams successfully install and run our program on their computers. Next, I will record the final presentation with my teammates.
Saturday | 2021-05-08 | 14:00 | 17:00 | 3 | Record the final presentation with my teammates. | One of the assignments of this project is to record a prerecord presentation on the poster. | I record the software architecture part of the presentation and change the content of this part in the poster, adding more examples like "implementing the sign-in function and searching method.".
|  |  | Total | 28