## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-03-22
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 10:00 | 15:00 | 5 | examine API | Our software will use API to get data from MS teams | Be able to get shifts from MS using API, next I will try to store it to database system
Tuesday |  | 9:00 | 16:00 | 7 | implementing database system between 2 groups | Team7 will prvided us data through database. It's important to test data sending/reciving through database | Be able to transfer data through database including searching, adding and deleting. Next we will discuss how to improve the performance the database
Wednesday |  | 14:00 | 17:00 | 3 | disccuss the structure of database with team 8 | We need database to store the data recived from course planner | Defined the format of data, Next we will have meeting with supervisor
Thursday |  | 14:30 | 16:00 | 1.5 | Meeting | Compulsory task of the course | Shared our idea among two groups. Redifined the method for implementing. Next I will continue to learn Python.
Friday |  | 13:30 | 17:30 | 4 | Learning Python Module | We use Python to develop the software, team 8 will provide us a web-spider modeule | Learned how to use python module. Next I will prepare for the presentation
Saturday |  | 18:20 | 22:20 | 4 | Presentation ppt | Our pitch presentation need a ppt | Comlepte the final version of ppt, Next I will practise the presentation
|  |  | Total | 24.5