## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-04-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 15:00 | 19:00 | 4 | set up Microsoft Graph development enviroment | Microsoft Graph is the gateway to data and intelligence in Microsoft 365 including Microsoft team. Our project will use its API | successfully set up the enviroment, next I will handle with the access token
Tuesday |  | 13:00 | 19:00 | 6 | Get an access token from the Microsoft identity platform. | The access token contains information about our software and the permissions it has for the resources and APIs available through Microsoft Graph. | successfully get the token from the Microsoft identity platform. Next I will register your app with the Microsoft identity platform
Wednesday |  | 12:00 | 18:30 | 6.5 | Register our software with the Microsoft identity platform | Registration integrates our software with the Microsoft identity platform and establishes the information | registered our software in the Azure portal, Next we will have meeting with supervisor
Thursday |  | 14:30 | 16:00 | 1.5 | Meeting | Compulsory task of the course | Clearfied the tasks during the midbreak, we decided to have a prototype after the midbreak. Next I will start to call the APIs.
Friday |  | 9:00 | 12:30 | 3.5 | Call the Microsoft Graph API by using the token | Our software will ues these API to get data from Microsoft team | Successfully read the data from Microsoft team. Next I will prepare for the business case.
Saturday |  | 9:00 | 12:30 | 3.5 | Set up graph Explorer | Graph Explorer is a web-based tool that we can use to build and test requests using Microsoft Graph APIs. | Successfully download and initialized the Graph Explorer, Next I will initialize the Microsoft team access
|  |  | Total | 25