## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-04-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 12:00 | 18:00 | 6 | Design the layout of the "shift" page. | This page is used to show the shifts to users. | I completed the shift.html, inheriting from home.html. Next, I will implement the function of sending requests.
Tuesday |  | 14:00 | 18:00 | 4 | Complete the function of sending a request to Microsoft Graph. | We need to send requests to Microsoft Graph to get data from users' accounts. | Implemented the function of sending requests. Next, I will implement the function of parsing JSON string.
Wednesday |  | 10:00 | 17:00 | 7 | Implement function of parsing JSON. | All packet received from Microsoft Graph is in the form of JSON. | Successfully parse the JSON string. Next, we will have meeting with our supervisor
Thursday |  | 14:30 | 16:00 | 1.5 | Regualr meeting | Get some advice fro our supervisor | We are clear about how the shifts are stored in the user's MS Team. Next, I will implement functions of sending GET teams and shifts.
Friday |  | 19:00 | 23:30 | 4.5 | Implementing the function of "shift" link. | Successfully initialize the home view. | But I found that with existing access token, I don't have access to the MS shift. Next, I will fix this problem.
Saturday |  | 13:00 | 16:00 | 3 | Create nested dictionaries to store the teams and shifts. | We need to store all the shifts and teams in a nested data structure. | Successfully created correct data structure to store shifts and teams information. Next, I will rendering shifts page to show this data.
|  |  | Total | 26