## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1786169 |  |  | Week starting: | 2021-05-24
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-24 | 9:00 | 18:00 | 9 | ◆Review the test plan ◆Implement specific deletion function. | A good test makes a good product. | Test our system this week, and keep trying to get a response from the client to clarify the requirements of the last meeting.
Tuesday | 2021-05-25 | 9:30 | 15:30 | 6 | ◆Test our system as planned. ◆Prepare survey for peer review. | Get feedback from real user is important and a covanient way is peer review casuse we all has project and can give feedback each other.
Wednesday | 2021-05-26 | 9:30 | 18:30 | 9 | ◆Review Django document to find out if there any code can be improved. | A good industry code should simple and esily to read. | It's hard to refactor our code, because we are not strict follow the logic of Django. I need to discuss with team members.
Thursday | 2021-05-27 | 9:30 | 16:30 | 7 | ◆Last meeting with client for testing and improvement. ◆Prepare for the poster. | A poster can show the project high level view. | Client is satisfied with our system and recomment us to improve the user interface.
Saturday | 2021-05-29 | 9:00 | 12:00 | 3 | ◆Prepare for the final report.
|  |  | Total | 34