## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1786169 |  |  | Week starting: | 2021-03-08
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08
Tuesday | 2021-03-09 | 19:00 | 21:30 | 2.5 | Learn about Microsoft Team Shift API library. | This our clinet requirment. He want us use this API to develop our shift system. | It will takes longer time than I expect to familiar how to use these API
Wednesday | 2021-03-10 | 10:00 | 17:00 | 7 | Learn about Microsoft Team Shift API library.
Thursday | 2021-03-11 | 14:00 | 15:00 | 1 | Weekly meeting | Get more information about this project from the client | We need to discuss with team 8 and allocate this project to two teams.
Thursday | 2021-03-11 | 15:00 | 20:00 | 5 | Research API manual and web scraper. | To find out which part should we choose | I would like to choose API part, because it will deploy all front end and back end, I think it will help me to find a relate job in the future.
Friday | 2021-03-12 | 18:30 | 21:00 | 2.5 | Research API manual and web scraper.
Saturday | 2021-03-13 | 15:00 | 17:00 | 2 | Meet with team 8 to decide how to allocate these two parts. |  | We are going to do the API part.
Sunday | 2021-03-14 | 9:00 | 13:00 | 4 | Learn about Microsoft Team Shift API library and SQL. |  | Should familiar with JSON and Rest
|  |  | Total | 24