## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1786169 |  |  | Week starting: | 2021-04-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-26 | 9:00 | 12:00 | 3 | Practice Django framework. | We decided move from desk app to web. Django is a framework for web with python. | Get familiar about how Django work.
Tuesday | 2021-04-27 | 8:30 | 14:30 | 6 | Modify the tutorial files to fit our project. | Some files in the tutorial are suitable for us to use in our project for basic webpage structure. | Failed to fetch data from School account on MS Team.
Wednesday | 2021-04-28 | 9:30 | 13:30 | 4 | Fetch data from our MS Teams by the MS graph API. | We have to compare the different between Teams shift and Course planner. So we should be able to get data from Teams. | Fuction finished, we can fetch shift from our team in Teams.
Thursday | 2021-04-29 | 13:00 | 18:00 | 5 | 1.weekly meeting with client. 2.milestone 1 report. |  | -We finished our report. -In the meeting we reflected our issue to our client and he was satisfied with our change.
Friday | 2021-04-30 | 13:30 | 17:00 | 3.5 | Learn about Javascript about Generator and advanced iteration. | I would like to create a tap for MS Teams which based on Javascript. It could make our project use convenient. | Understand how generator work and what is advanced iteration.
Saturday | 2021-05-01 | 9:00 | 12:00 | 3 | Learn about Javascript about module. |  | Understand how module work in Javascript.
|  |  | Total | 24.5