## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1786169 |  |  | Week starting: | 2021-05-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-10 | 8:30 | 12:00 | 3.5 | Review the documentation of Django about how it work and what function can we use. | We decided move from desk app to web. Django is a framework for web with python. | To modify the tutorial file to fit our project.
Tuesday | 2021-05-11 | 9:30 | 15:30 | 6 | Implement function to get shift from Teams. | Some files in the tutorial are suitable for us to use in our project for basic webpage structure. | We can only fetch shifts from teams which created by ourself. We will try to fix this later, but it still may be fail due to some irresistible factor.
Tuesday | 2021-05-11 | 17:00 | 17:20 | 0.3 | Meet with Cruz. |  | We need to work harder and quickly to catch other groups' progress. We will more hard on our project because we want a high score.
Wednesday | 2021-05-12 | 9:30 | 23:30 | 14 | Review the documentation of Django about how it work and what function can we use. |  | Understood how form and template work, known what are request and response objects.
Thursday | 2021-05-13 | 9:30 | 16:30 | 7 | 1.weekly meeting with client. 2.To finish basic interface of the system. |  | -We finished basic interface of the system. -In the meeting we reflected our issue to our client and potential issue in the future. He was satisfy with our work.
Saturday | 2021-05-15 | 9:00 | 22:00 | 13 | Modify the code with Django ducmentation. | We need to implement the search function and best possible give choice to client to update or delete the shift. | Some query parameters are not avaliable for specified endpoint, so we have to modify the data structure manually.
Sunday | 2021-05-16 | 7:00 | 22:00 | 15 | Modify the code with Django ducmentation. Create delete function. | We have done some code, but we still need to make our code finely and easy to understand. | Didn’t finish delete shift funtion finely, should be finished next day.
|  |  | Total | 58.8