## Week2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 11:00 | 15:00 | 4 | Research on programming language | programming skill | new to python, have to get along with it
Tuesday | 2021-03-09 | 9:00 | 14:00 | 5 | Pitch review | presentation skill | body language during pitch
Wednesday | 2021-03-10 | 9:00 | 14:00 | 5 | Research on database | basic knowledge of database
Thursday | 2021-03-11 | 13:00 | 17:00 | 4 | Weekly meeting, task review | To get more information from client | Reseach on Microsoft Team Shift, and web scapper, we have to split the work with Team 8
Friday | 2021-03-12 | 14:00 | 18:00 | 4 | Reseach on Microsoft Team Shift, and web scapper | Team work allocation | To decide which part to take
Saturday | 2021-03-13 | 15:00 | 17:00 | 2 | Split the task |  | check out API info
|  |  | Total | 24

## Week3
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 10:00 | 15:00 | 5 | Review Microsoft Graph & Teams documentries | API knowledge | Get along with MS Graph & Teams
Tuesday | 2021-03-16 | 11:00 | 14:00 | 3 | Pitch checklist review | presentation skill | make sure audience understand the context in a given time
Wednesday | 2021-03-17 | 23:00 | 16:00 | 5 | Review Git & Github | repository for pair programming | we could set up relative app on Git repository
Thursday | 2021-03-18 | 14:30 | 18:00 | 3.5 | Weekly meeting, task clarification | To get more information from client | Research on MS Shift API
Friday | 2021-03-19 | 14:00 | 17:00 | 3 | Reseach on Microsoft Team Shift, and Javascript | Build up knowledge | slides preparation
Saturday | 2021-03-20 | 14:30 | 19:00 | 4.5 | Pitch preparation | Pitch slide | Presentation draft
|  |  | Total | 24

## Week4
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-22 | 9:00 | 15:00 | 6 | structure pitch | pitch presentation | better performance on pitch
Tuesday | 2021-03-23 | 10:00 | 14:00 | 4 | trial on Mircosoft Team Shift | get idea to design Shift API | learning the API function
Wednesday | 2021-03-24 | 12:00 | 16:00 | 4 | Review Javascript | programming skill | We might decide to use javascript stead of python
Thursday | 2021-03-25 | 14:30 | 19:00 | 4.5 | Weekly meeting, standardizing programming language with team 8 | report progress and obtain feedback from supervisor | Refine pitch presentation & milestone planning
Friday | 2021-03-26 | 13:00 | 17:00 | 4 | Reseach on Microsoft Graph API | Build up knowledge | programming skill
Saturday | 2021-03-27 | 15:30 | 19:00 | 3.5 | Pitch revision | Pitch slide | Presentation final draft
|  |  | Total | 26

## Week5
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-29 | 9:00 | 14:00 | 5 | structure pitch speech | pitch presentation | preparation on pitch speech
Tuesday | 2021-03-30 | 10:00 | 14:00 | 4 | Pitch presentation recording | pitch presentation | well-performed pitch presentation
Wednesday | 2021-03-31 | 23:00 | 14:00 | 3 | pitch rehersal | pitch presentation | finalize the pitch
Thursday | 2021-04-01 | 13:00 | 18:00 | 5 | Convert pitch speech into text | construct business case | preparation on business case
Friday | 2021-04-02 | 12:00 | 15:00 | 3 | milestone planning | plan for milestone | milestone draft
Saturday | 2021-04-03 | 8:00 | 13:30 | 5.5 | Refine business case & milestone planning | Business case & milestone planning | Well-prepared business case & milestone planning
|  |  | Total | 25.5

## Week6
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 | 9:00 | 11:00 | 2 | constructing the api | programming | need a better structure of it
Tuesday | 2021-04-06 | 11:00 | 14:00 | 3 | Python practicing | programming | get used to the language
Wednesday | 2021-04-07 | 21:00 | 14:00 | 5 | Watch other teams’ presentation | pitch discussion | Ask to other team if any question
Thursday | 2021-04-08 | 14:00 | 18:00 | 4 | Ask at least one question to other teams | pitch discussion | Better understanding of other projects
Friday | 2021-04-09 | 10:00 | 15:00 | 5 | Learn how to build Microsoft Teams app | API implementation | Better understanding of the API construction
Saturday | 2021-04-10 | 12:00 | 15:30 | 3.5 | Learn how to build Microsoft Teams app | API implementation | Better understanding of the API construction
|  |  | Total | 22.5

## Mid-break
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | Mid-Break
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-19 | 9:00 | 13:00 | 4 | Research on Microsoft Graph & Azure | Constructing Microsoft Graph API | understand the process of API registration
Tuesday | 2021-04-20 | 10:00 | 15:00 | 5 | first trial to get Microsoft Teams detail | API design | getting user token info back
Wednesday | 2021-04-21 | 23:00 | 14:00 | 3 | token retrieve from Microsoft Graph API | API implementation | API design
Thursday | 2021-04-22 | 13:00 | 18:30 | 5.5 | syn the info from web api to Microsoft Shifts | API construct | preparation on business case
Friday | 2021-04-23 | 12:00 | 16:00 | 4 | learning on Daemon app. | API design | integrate web app to daemon app
Saturday | 2021-04-24 | 9:00 | 13:00 | 4 | learning on design Daemon app. | API design | better understanding to implement API
|  |  | Total | 25.5

## Week7
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-26 | 9:00 | 14:00 | 5 | Get authentication tokens from Microsoft Teams | To read the data from Microsoft Teams | Generated the tokens that include access to Microsoft Teams Shifts API
Tuesday | 2021-04-27 | 11:00 | 15:00 | 4 | Microsoft Graph API implementation | To display the data we fetched from Microsoft Teams | Built a timetable on our web page to display data
Wednesday | 2021-04-28 | 10:00 | 14:00 | 4 | Register our application with the Microsoft identity platform - Microsoft Azure | To make our app working online | Registered our application on Azure and successfully got the application (client) ID and client secret
Thursday | 2021-04-29 | 13:00 | 18:00 | 5 | Milestone report | milestone management | milestone report draft
Friday | 2021-04-30 | 22:00 | 14:00 | 5 | Revise Milestone report | milestone management | Revise sentenses and make it more clear
Saturday | 2021-05-01 | 21:00 | 12:00 | 3 | Revise Milestone report | milestone management | make some improvement in each activities, as we did not did a good job on milestone 1, added more detail
|  |  | Total | 26

## Week8
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-03 | 17:00 | 20:00 | 3 | Revise Milestone 1 report | Covered everything what we did to milestone 1 | Added more details on activities, conclued what we have achieved, and reflected project progressing
Tuesday | 2021-05-04 | 9:00 | 14:00 | 5 | Revise API to read Shifts groups | To get every course of roster for the client | To confirm the format of the roster with the client
Wednesday | 2021-05-05 | 11:00 | 13:00 | 2 | Review lecture material of week 7 and week 8, prepare for milestone 2 plan | We can follow the milestone 2 plan to finish our project | Milestone 2 plan should cover all the things for the following 4 weeks
Thursday | 2021-05-06 | 13:00 | 17:30 | 4.5 | Weekly meeting & Milestone 2 planning | Milestone for the second half of the project | Setting milestone for the following 4 weeks
Friday | 2021-05-07 | 10:00 | 16:00 | 6 | Revise milestone 2 | Added more details on each activities and milestone | Make sure everything about the project is included
Saturday | 2021-05-08 | 13:00 | 17:00 | 4 | Fixing API code | Make sure users can login the web app | Fixed some bugs on the html file
|  |  | Total | 24.5

## Week9
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-10 | 17:00 | 20:00 | 3 | Review lecture material of week 9, prepare for testing plan | Learn what is the test strategy, and how is the test executing | We should have understood what will be tested and why, how will test results be recorded
Tuesday | 2021-05-11 | 17:00 | 19:00 | 2 | Get feedback on milestone 2 and review with Cruz & team meeting for the next action | Get to know what is the problem our team has and review our milestone 2 | We all need to put more effort on the project and everyone of us needs to be more proactive. Next: we will consider how to integrate the part that Team 8 will provide to us
Wednesday | 2021-05-12 | 11:00 | 18:00 | 7 | Implement matching function to compare the difference between course planner website and Mircosoft Teams Shifts | To display what is matched and what is not correct between the course planner website and Microsoft Teams Shifts. Ex: Time, location | We have completed to identify what is matched between a template data and Microsoft Teams Shifts, once we integrate the code with Team 8, it should be working to compare the date from course planner and Mircosoft Teams Shifts
Thursday | 2021-05-13 | 10:00 | 16:00 | 6 | Weekly meeting & Integrate parts from Team 8’s web-scraper | As we are working with other team, we need to merge, and integrate both team code together | We have implemented a delete function for user to delete unmatch shifts on Mircosoft Teams Shifts. Next action: we need to tell Team 8 what they need to fix in order to get everything working because some format are not integratable with our code
Friday | 2021-05-14 | 13:00 | 17:00 | 4 | Debugging if any error occurs on the system | Ensure our system can work on any circumstances | Our system can handle if no Mircosoft Teams exist and if no Shifts is existed, our system will report problem to user on the our web
Saturday | 2021-05-15 | 14:00 | 17:00 | 3 | Draft test plan | Draft project overview & scope of the test plan | Roughly draft the project overview & scope. Next: we need to think about test strategy & test execution.
|  |  | Total | 25

## Week10
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-17 | 13:00 | 18:00 | 5 | Draft testing plan & review lecture slides | Testing plan can keep us checking our software is bulit properly and make sure we meet client requirements | Drafted a testing plan, completed most of the parts. Next: merge the matching function with Team 8 web scraper
Tuesday | 2021-05-18 | 14:00 | 17:00 | 3 | Adjusting the web scraper | To match all the differences between Mircosoft Shifts and the course planner, our software must need to integrate with Team 8's web scraper | Integrated both teams code together, so that our software can use the web scraper function as well
Wednesday | 2021-05-19 | 9:00 | 14:00 | 5 | Debugging on matching function | matching function to show the differences between Mircosoft Shifts and the course planner | Outcome: adjust our code to fit in the matching function with web scraper.
Thursday | 2021-05-20 | 12:00 | 17:00 | 5 | Weekly meeting & preparing test case | Show our latest version of software to the client. Executing some test cases to make sure our software is working correctly | Outcome: client satisfied with our product, after we demostrated all the functionality of the system. Next: improve our software so it can be more user-friendly. Some errors are identified, we need to fix it asap.
Friday | 2021-05-21 | 13:00 | 18:00 | 5 | Fixing some abnormal behavior: matching function needs to be more accruate | To develop our matching function, so that the users can search and compare the differences more concisely. | Organizing some code, fixing some bugs, so it can improve the software performance
Saturday | 2021-05-22 | 14:00 | 17:00 | 3 | Revision on the testing plan | Need to specify some test case and add more detail on each part, so our software could be well prepared. | Outcome: specified some test cases and added gantt chart, so reviewer can have better picture of what we have tested.
|  |  | Total | 26

## Week11
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-24 | 17:00 | 21:00 | 4 | Review lecture recording & slides, Revision on testing plan | A well covered test plan can prevent unexpected bug. Added testing schedule on appendix and added more details on each test. | Outcome: identify possible risks and schedule to fix it. Next: execute testing plan and fix the bugs
Tuesday | 2021-05-25 | 11:00 | 16:00 | 5 | Handle multiple shifts in one course | Our software could be able to handle if the user wants to assign multiple shifts within one course | Outcome: adjust some parameter, so our software would not only restrict to have only one shift at a time
Wednesday | 2021-05-26 | 11:00 | 15:00 | 4 | Create a project survey | A project survey can collect feedback from peer, so we can adjust our user interface before releasing final version | Outcome: receive some feedback, so we can improve the user experience with our softeware. Next: add some instruction to guide the user, explain how our app works and how to use
Thursday | 2021-05-27 | 14:00 | 18:00 | 4 | Weekly meeting, task review | Demostrate our latest version of software to the client, and received feedback from the client | Outcome: Our client satisfied with our product, and as we agreed before creating new shifts is not applicated on this project due to account restriction. This would be the last meeting with our client, if something happens, arrange meeting with client before next Thursday morning.
Friday | 2021-05-28 | 13:00 | 18:00 | 5 | Display assigned staff on the table | Software can show what staff assigned on that shifts | Outcome: improve user experience, the user can know who is assigned on that shifts, so the user can manage the Shifts more efficient and convenient.
Saturday | 2021-05-29 | 14:00 | 17:00 | 3 | Detailing the web page design & user guide, and debug | Polish some web page design, added a user guide for first time users and provide instruction | Outcome: Well design web page and clear instruction can improve user experience.
|  |  | Total | 25