## Week2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 11:00 | 15:00 | 4 | Research on programming language | programming skill | new to python, have to get along with it
Tuesday | 2021-03-09 | 9:00 | 14:00 | 5 | Pitch review | presentation skill | body language during pitch
Wednesday | 2021-03-10 | 9:00 | 14:00 | 5 | Research on database | basic knowledge of database
Thursday | 2021-03-11 | 13:00 | 17:00 | 4 | Weekly meeting, task review | To get more information from client | Reseach on Microsoft Team Shift, and web scapper, we have to split the work with Team 8
Friday | 2021-03-12 | 14:00 | 18:00 | 4 | Reseach on Microsoft Team Shift, and web scapper | Team work allocation | To decide which part to take
Saturday | 2021-03-13 | 15:00 | 17:00 | 2 | Split the task |  | check out API info
|  |  | Total | 24

## Week3
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 10:00 | 15:00 | 5 | Review Microsoft Graph & Teams documentries | API knowledge | Get along with MS Graph & Teams
Tuesday | 2021-03-16 | 11:00 | 14:00 | 3 | Pitch checklist review | presentation skill | make sure audience understand the context in a given time
Wednesday | 2021-03-17 | 23:00 | 16:00 | 5 | Review Git & Github | repository for pair programming | we could set up relative app on Git repository
Thursday | 2021-03-18 | 14:30 | 18:00 | 3.5 | Weekly meeting, task clarification | To get more information from client | Research on MS Shift API
Friday | 2021-03-19 | 14:00 | 17:00 | 3 | Reseach on Microsoft Team Shift, and Javascript | Build up knowledge | slides preparation
Saturday | 2021-03-20 | 14:30 | 19:00 | 4.5 | Pitch preparation | Pitch slide | Presentation draft
|  |  | Total | 24

## Week4
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-22 | 9:00 | 15:00 | 6 | structure pitch | pitch presentation | better performance on pitch
Tuesday | 2021-03-23 | 10:00 | 14:00 | 4 | trial on Mircosoft Team Shift | get idea to design Shift API | learning the API function
Wednesday | 2021-03-24 | 12:00 | 16:00 | 4 | Review Javascript | programming skill | We might decide to use javascript stead of python
Thursday | 2021-03-25 | 14:30 | 19:00 | 4.5 | Weekly meeting, standardizing programming language with team 8 | report progress and obtain feedback from supervisor | Refine pitch presentation & milestone planning
Friday | 2021-03-26 | 13:00 | 17:00 | 4 | Reseach on Microsoft Graph API | Build up knowledge | programming skill
Saturday | 2021-03-27 | 15:30 | 19:00 | 3.5 | Pitch revision | Pitch slide | Presentation final draft
|  |  | Total | 26

## Week5
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-29 | 9:00 | 14:00 | 5 | structure pitch speech | pitch presentation | preparation on pitch speech
Tuesday | 2021-03-30 | 10:00 | 14:00 | 4 | Pitch presentation recording | pitch presentation | well-performed pitch presentation
Wednesday | 2021-03-31 | 23:00 | 14:00 | 3 | pitch rehersal | pitch presentation | finalize the pitch
Thursday | 2021-04-01 | 13:00 | 18:00 | 5 | Convert pitch speech into text | construct business case | preparation on business case
Friday | 2021-04-02 | 12:00 | 15:00 | 3 | milestone planning | plan for milestone | milestone draft
Saturday | 2021-04-03 | 8:00 | 13:30 | 5.5 | Refine business case & milestone planning | Business case & milestone planning | Well-prepared business case & milestone planning
|  |  | Total | 25.5

## Week6
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 | 9:00 | 11:00 | 2 | constructing the api | programming | need a better structure of it
Tuesday | 2021-04-06 | 11:00 | 14:00 | 3 | Python practicing | programming | get used to the language
Wednesday | 2021-04-07 | 21:00 | 14:00 | 5 | Watch other teams’ presentation | pitch discussion | Ask to other team if any question
Thursday | 2021-04-08 | 14:00 | 18:00 | 4 | Ask at least one question to other teams | pitch discussion | Better understanding of other projects
Friday | 2021-04-09 | 10:00 | 15:00 | 5 | Learn how to build Microsoft Teams app | API implementation | Better understanding of the API construction
Saturday | 2021-04-10 | 12:00 | 15:30 | 3.5 | Learn how to build Microsoft Teams app | API implementation | Better understanding of the API construction
|  |  | Total | 22.5

## Mid-break
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | Mid-Break
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-19 | 9:00 | 13:00 | 4 | Research on Microsoft Graph & Azure | Constructing Microsoft Graph API | understand the process of API registration
Tuesday | 2021-04-20 | 10:00 | 15:00 | 5 | first trial to get Microsoft Teams detail | API design | getting user token info back
Wednesday | 2021-04-21 | 23:00 | 14:00 | 3 | token retrieve from Microsoft Graph API | API implementation | API design
Thursday | 2021-04-22 | 13:00 | 18:30 | 5.5 | syn the info from web api to Microsoft Shifts | API construct | preparation on business case
Friday | 2021-04-23 | 12:00 | 16:00 | 4 | learning on Daemon app. | API design | integrate web app to daemon app
Saturday | 2021-04-24 | 9:00 | 13:00 | 4 | learning on design Daemon app. | API design | better understanding to implement API
|  |  | Total | 25.5

## Week7
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1797912 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-26 | 9:00 | 14:00 | 5 | Get authentication tokens from Microsoft Teams | To read the data from Microsoft Teams | Generated the tokens that include access to Microsoft Teams Shifts API
Tuesday | 2021-04-27 | 11:00 | 15:00 | 4 | Microsoft Graph API implementation | To display the data we fetched from Microsoft Teams | Built a timetable on our web page to display data
Wednesday | 2021-04-28 | 10:00 | 14:00 | 4 | Register our application with the Microsoft identity platform - Microsoft Azure | To make our app working online | Registered our application on Azure and successfully got the application (client) ID and client secret
Thursday | 2021-04-29 | 13:00 | 18:00 | 5 | Milestone report | milestone management | milestone report draft
Friday | 2021-04-30 | 22:00 | 14:00 | 5 | Revise Milestone report | milestone management | Revise sentenses and make it more clear
Saturday | 2021-05-01 | 21:00 | 12:00 | 3 | Revise Milestone report | milestone management | make some improvement in each activities, as we did not did a good job on milestone 1, added more detail
|  |  | Total | 26