## Week2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-03-08
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 11:00 | 14:00 | 3 | Searching information about the project,Contacting supervisor. | To complete the project, we need lots of information regarding software development. We have to think which programming tools/languages/framework is suitable for our project. | I found that Python is sutable for develop web-scraper which will be used in our projecct to extract the data from websites. On the other hand, Java has high level of portability. It suit for us because the software we are developing is required to run on different platforms. Next I will examine and learn these skills I need.
Tuesday | 2021-03-09 | 10:00 | 2:00 | 4 | Learining MySQL | After getting the data, we have to store these data. MySQL is a database system to fulfill this. | Uderstand basic operation of MySQL. Learned how to use it to store the data we get from target websites. Next I will learn Python and ask our supervisor for a meeting.
Wednesday | 2021-03-10 | 19:00 | 23:00 | 4 | Learining Pyhon. Schedule the first meeting. | Pyhon is the programming languge used to develop web-scraper. Our superviser will clear his demand. | Learnd basic element of Pyhon, including configuring programming environment, basic grammar, varables and operations in Python. Arranged the first meeting with supervisor/client.Next we will have a meeting with our supervisor and I will continue to learn more about Python.
Thursday | 2021-03-11 | 14:00 | 15:00 | 1 | Meeting. Discuss what we get from supervisor with our team members. | The user demand will be our target of the whole project. | Get the user demand from our client. Share our idea on how to meet these demands with our team members.I'ss continue to learn Python
Friday | 2021-03-12 | 13:00 | 22:00 | 9 | learning Python Syntax | Python will be used in web-scraper programme | Uderstand the function, list/tuple/dict/set in Python. Next Iwill review Java.
Saturday | 2021-03-13 | 9:00 | 13:00 | 4 | Reviewing Java | Java will be used in API | Reviewed JAVA which I have learned 1 year ago. Next I will learn Python.
|  |  | Total | 25

## Week3
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-03-08
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 10:00 | 18:00 | 8 | Python practice and lecture | Python is the programming language for this project | Get more familiar with Python. Get lots of information about pitch presentation. Next action is trying to use the APIs
Tuesday |  | 9:00 | 20:00 | 11 | Try to practice on Microsoft Graph API | Our software uses API to get data from Microsoft Team | Created a webpage that can read data from Microsoft calendar. Next action is to create an agenda for next meeting.
Wednesday |  | 18:00 | 21:00 | 2 | Learning HTML and Preparing next meeting | Html will be useful to use Microsoft API. We will get lots of information from our client through meeting | Be able to set up a web layout using HTML. Completed the agenda for next meeting and send it to our supervisor. Next we will have meeting at Thursday.
Thursday |  | 14:30 | 15:30 | 1 | Meeting with client | Uderstanding the client demands is necessary | Our client spcified his demand. Next is to officially document the demands for development purpose
Friday |  | 13:30 | 14:30 | 1 | Meeting with team members | Exchange our ideas regarding the software development | Be more clear about the client requirement. Next is to create the ppt draft
Saturday |  | 14:30 | 19:00 | 4.5 | Hold a face-toface team meeting to complete pitch presentation ppt | The slides are required by project | Complete a draft of ppt and send it to superviser, arranged the presentation.Next is to prepare for the presentation
|  |  | Total | 27.5

## Week4
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-03-22
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 10:00 | 15:00 | 5 | examine API | Our software will use API to get data from MS teams | Be able to get shifts from MS using API, next I will try to store it to database system
Tuesday |  | 9:00 | 16:00 | 7 | implementing database system between 2 groups | Team7 will prvided us data through database. It's important to test data sending/reciving through database | Be able to transfer data through database including searching, adding and deleting. Next we will discuss how to improve the performance the database
Wednesday |  | 14:00 | 17:00 | 3 | disccuss the structure of database with team 8 | We need database to store the data recived from course planner | Defined the format of data, Next we will have meeting with supervisor
Thursday |  | 14:30 | 16:00 | 1.5 | Meeting | Compulsory task of the course | Shared our idea among two groups. Redifined the method for implementing. Next I will continue to learn Python.
Friday |  | 13:30 | 17:30 | 4 | Learning Python Module and set up Django project | We use Python to develop the software, team 8 will provide us a web-spider modeule | successfully set our project in Django framework and learned how to use python module. Next I will prepare for the presentation
Saturday |  | 18:20 | 22:20 | 4 | Presentation ppt | Our pitch presentation need a ppt | Comlepte the final version of ppt, Next I will practise the presentation
|  |  | Total | 24.5

## Week5
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-03-29
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 13:00 | 18:00 | 5 | Learning Python class | The data read from course planner is in the form of class | learned how to use Python class, next I will learn Python output
Tuesday |  | 19:00 | 23:00 | 4 | learning Python output | the data read from course planner will be output to a file | learned how to write a file using Python. Next we will prepare for next meeting
Wednesday |  | 14:00 | 17:00 | 3 | Have meeting and collected all questions we have now | It is improtant for us to be clear about the customer requirement | Summarized all question, Next we will have meeting with supervisor
Thursday |  | 14:30 | 16:00 | 1.5 | Meeting | Compulsory task of the course | Shared our idea among two groups, Lots of question regarding the requirement are cleared. Next I will start to record pitch presentation.
Friday |  | 14:00 | 19:30 | 5.5 | Prepare and record pitch presentation | Compulsory task of the course | Submitted our pitch presentation. Next I will prepare for the business case.
Saturday |  | 8:00 | 13:30 | 5.5 | Business case | Compulsory task of the course | Comlepte the final version of Business case, Next I will practise Java
|  |  | Total | 24.5

## Week6
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-04-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 15:00 | 19:00 | 4 | set up Microsoft Graph development enviroment | Microsoft Graph is the gateway to data and intelligence in Microsoft 365 including Microsoft team. Our project will use its API | successfully set up the enviroment, next I will handle with the access token
Tuesday |  | 13:00 | 19:00 | 6 | Get an access token from the Microsoft identity platform. | The access token contains information about our software and the permissions it has for the resources and APIs available through Microsoft Graph. | successfully get the token from the Microsoft identity platform. Next I will register your app with the Microsoft identity platform
Wednesday |  | 12:00 | 18:30 | 6.5 | Register our software with the Microsoft identity platform | Registration integrates our software with the Microsoft identity platform and establishes the information | registered our software in the Azure portal, Next we will have meeting with supervisor
Thursday |  | 14:30 | 16:00 | 1.5 | Meeting | Compulsory task of the course | Clearfied the tasks during the midbreak, we decided to have a prototype after the midbreak. Next I will start to call the APIs.
Friday |  | 9:00 | 12:30 | 3.5 | Call the Microsoft Graph API by using the token | Our software will ues these API to get data from Microsoft team | Successfully read the data from Microsoft team. Next I will prepare for the business case.
Saturday |  | 9:00 | 12:30 | 3.5 | Set up graph Explorer | Graph Explorer is a web-based tool that we can use to build and test requests using Microsoft Graph APIs. | Successfully download and initialized the Graph Explorer, Next I will initialize the Microsoft team access
|  |  | Total | 25

## midbreak
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1785394 |  | Week starting: | 2021-04-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 15:00 | 19:00 | 4 | Design the layout of the app using html. | Our app will present to our users by a web page. | Complete an HTML file of the home page. Next, I will add bootstrap
Tuesday |  | 13:00 | 19:00 | 6 | Adding bootstrap for simple styling | Adding bootstrap for simple styling | Successfully add bootstrap to the HTML file. Next, I will add some icons.
Wednesday |  | 12:00 | 17:30 | 5.5 | Adding Fabric Core for some simple icons. | Improve the user experience by using lots of Icons to show the function of each button. | Added lots of functions, making our app more beautiful. Next, we will specify the style of HTML
Thursday |  | 14:30 | 16:00 | 1.5 | Adding CSS file. | The style of font and size of our web page would affect our users' experience. | An CSS flie to clarify the style of our HTML page. Next, I will implement some functions of those links on our page.
Friday |  | 19:00 | 23:30 | 4.5 | Implementing the function of "home" link. | Successfully initialize the home view. | But I found that with existing access token, I don't have access to the MS shift. Next, I will fix this problem.
Saturday |  | 14:00 | 18:00 | 4 | Correct the access token. | We need the correct access token to get data from users' accounts. | Get a valid access token that can access to shift. Next, I will continue to implement the functions of our app.
|  |  | Total | 25.5